## Workplan
Work plan
Outcome
Output |  | Annual target/s |  |  | List of activities | [12 empty] | PUNO/s involved | Implementing partner/s involved
| Baseline | 2020 | 2021 | 2022 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Output 1: A Social Protection Policy submitted to the Government of Angola for endorsement and approval | 0 | *Report of diagnosis and cost estimate, *Alternatives for fiscal space for social protection assessment available | 1 Costed social protection document |  | Carry out a diagnosis of the Angolan social protection system, using the CODI-ISPA tool for assessing existing schemes and programs, legal framework, population covered, content and level of benefits, gaps, coordination mechanisms, etc | [12 empty] | ILO UNICEF | MASFAMU MAPTSS MIN OF PLANNING MIN FINANCE ILO COMMISSION INSS CSO IMF WB | bar: Q1 to Q2
Evaluate the budgeting cycle according to international standards (like PEFA) and the four main phases in which the cycle is divided | bar: Q1 to Q2
Identify the policy options for strengthening and extending social protection towards universal coverage and improving the efficiency and effectiveness of social protection spending | bar: Q3
Present scenarios for different policy alternatives and different approaches to roll out (phases / timing / regional coverage etc) | bar: Q3 to Q4
Formulate the methodological approach and assumptions of the costing model | bar: Q4
Collect relevant macro, financial, utilization and socioeconomic data and estimate key parameters | bar: Q4
Estimate the costs of the policy options identified in the last activity of the previous step | bar: Q1
Estimate the financing gaps in social protection for achieving SDG target | bar: Q1
Identify and assess financing options for the social protection system so to close the gap based on economic, fiscal, social and political feasibility | bar: Q1
Organize national consultations for the validation and prioritization of the policy options, roll-out options and the medium-term plan for implementation and funding | bar: Q2
Review the existing draft social protection plan and write down a new policy document based on the results of the social protection evaluation, the budgeting assessment, the cost of the different policy alternatives, the fiscal space assessment and social dialogue. This document may include aspects such as: | bar: Q2 to Q3
Preparation of an advocacy strategy for political endorsement of the social protection policy, strategy and financial | bar: Q2 to Q4
Output 2: A series of strategic actions are conducted for the preliminary implementation of a performance-based budgeting model in social protection institutions | 0 | *The architecture of the Performance based Budgeting Committee is define *The budgeting cycle is evaluated | *A methodological note the PBB is available * An action plan fand a booklet on PBB are available | Capacity building on PBB | Prepare a decree with the creation of the Performance-based Budgeting Committee integrated with staff members of the Ministry of Finance, the Ministry of Economy and Planning, and the social protection sector | [12 empty] | ILO UNICEF | bar: Q3 to Q4
Evaluate the budgeting cycle according to international standards (like PEFA) and the four main phases in which the cycle is divided | bar: Q3 to Q1
Develop a methodological and conceptual note on the theoretical fundamentals of performance-based budgeting, including components | bar: Q2 to Q3
Prepare a booklet on “how-to” implement performance-based budgeting in the social protection sector | bar: Q3
Design a training program for the members of the Budgeting Commission | bar: Q4 to Q1
Formulate an Action Plan with pilot test included to launch performance-based budgeting in a sample of social institutions. | bar: Q2 to Q3
Output 3: Coordination of the social protection system is improved | 0 | *Report of mapping of existing coordination mechanisms * The architecture of the multisectorial coordination Committee is proposed * A normative piece for the coordination Committee is drafted | *The National coordination Committee is created * 2 meetings of the coordination Committee | 2 meetings of the coordination Committee | Carry out a mapping of coordination mechanisms in social protection and evaluate using SWOT analysis or similar | [12 empty] | ILO UNICEF | ASFAMU MAPTSS MIN OF PLANNING MIN FINANCE ILO COMMISSION CSO INSS | bar: Q2
Propose an architecture for a multisectoral National Committee for Social Protection | bar: Q3
Define and set up mechanisms of articulation between social protection institutions and programmes, including the program for ex-combatant; | bar: Q3 to Q4
Develop the multisectorial national Committee's operating tools and procedures | bar: Q4
Develop advocacy for the establishment of the multisectorial national Committee | bar: Q4
Prepare the required normative (either an organic law, presidential decree or similar figure) to provide the Committee with legal support | bar: Q1 to Q4
Support the functioning of the multisectorial national Committee | bar: Q1 to Q4
Facilitate inter-ministerial dialogues as well as national social dialogue to discuss social protection policy options, efficiency, effectiveness and impact matters and fiscal space | bar: Q4; Q3; Q3
Output 4: Public institutions with better capacities to improve budgeting and service delivery | 0 | *15 staffing duly trained in performance-based budgeting aspects *20 staffing duly trained in strategies to enhance service delivery capacity * 10 staffing duly trained in social protection statistics for policy purposes | *20 staffing duly trained in performance-based budgeting aspects *30 staffing duly trained in strategies to enhance service delivery capacity * 10 staffing duly trained in social protection statistics for policy purposes | *15 staffing duly trained in performance-based budgeting aspects *50staffing duly trained in strategies to enhance service delivery capacity * 10 staffing duly trained in social protection statistics for policy purposes | Apply a country-based diagnostic tool to understand the institutional and staffing profile skills to undertake evidence-based planning and budgeting, efficient and timely spending and accurate financial reporting | [12 empty] | ILO UNICEF | ASFAMU MAPTSS MIN OF PLANNING MIN FINANCE ILO COMMISSION CSO INSS | bar: Q3 to Q4
Prepare a Capacity Building Plan for social protection institutions, the Ministry of Planning, the Ministry of Finance and some municipalities | bar: Q1 to Q2
Implement different capacity building activities according to previous Plan | bar: Q4; Q2; Q4
Design and support the implementation of a social security scheme for workers in informal and rural sector | bar: Q3 to Q4
Assess the effects of capacity building on the level of knowledge and skills of the staffing | bar: Q1; Q4
Train MASFAMU to incorporate the cash transfer program in line with the municipalization of social services as part of its portfolio of projects; | bar: Q3 to Q4
Train the ILO Commission with the contents of the advocacy strategy to promote the extension of social security. | bar: Q3 to Q4