## Social Protection
Work plan 2012: SOCIAL PROTECTION
Outputs/Goals |  | Activities | Leading agency | Start date | End date
A | Ensuring gender, HR, HIV sensitive social protection | 1. Debriefing on studies related to gender, human rights, and social protection | UN Women | 1st Quarter | 4th Quarter
B | Strengthening coordination on SP within the UN | 1. Updating matrix of UN SP activities | SP Sub-Working Group (Chair) | 1st Quarter | 2nd Quarter
|  | 2. Putting social protection materials from the assessment study on the website | UNRC Office | 1st Quarter | 4th Quarter
|  | 3. Sharing of agencies specific social protection related activities (e.g. scoping missions, regional missions etc) | To be identified by theme | 1st Quarter | 4th Quarter
|  | 4. Review of UNPDF joint programmes from a SP perspective (e.g. YEP) | SP Sub-Working Group (Chair) | 1st Quarter | 4th Quarter
|  | 5. Explore development of UN joint programme on SP | SP Sub-Working Group (Chair) | 1st Quarter | 2nd Quarter
C | Strengthening coordination on Sp with Government, CSOs and DPs | 1. Sharing information, plan, and studies through meetings and other activities (e.g. inviting GIZ to share the gender checklist) | To be identified by theme | One per quarter (3 to 4 per year)
|  | 2. Coordination with UN Human Rights Working Group on government plans to implement convention on the rights of disabled people | SP Sub-Working Group (Chair) | 1st Quarter | 4th Quarter
|  | 3. Joint meetings, awareness raising, capacity building with other UN agencies (e.g. with HR group, gender group) | SP Sub-Working Group (Chair) | 1st Quarter | 4th Quarter
|  | 4. Involvement of UN in the Global Pulse for the monitoring of vulnerable groups | UNDP | 1st Quarter | 4th Quarter